## Product Backlog
SPRINT #1 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
1 | As a super admin, I want to add a new user so that the user can access/use the ND Telemedicine platform. | 1.1 1.2 1.3 1.4 | Implement Login page for Admin Develop add user function Implement add user page Set database Code peer review Regression testing |  | X
2 | As a super admin, I want to update user details so that user details are up to date. | 2.1 2.2 2.3 2.4 | Develop update user function Update Database Code peer review Regression testing |  | X
3 | As a super admin, I want to archive a user so that the user cannot access the ND Telemedicine platform. | 3.1 3.2 3.3 3.4 | Develop archive user function Update Database Code peer review Regression testing |  | X
4 | As a patient i want to make an account on the app so that i can access the services of the app such as having contact with a doctor | 4.1 4.2 4.3 4.4 | Implement Patient register page Update database Code peer review Regression testing |  | X
5 | As a Patient i want to add health information about me, so that my doctor can see my current health condition | 5.1 5.2 5.3 5.4 | Implement health page Update database Code peer review Regression testing |  | X
6 | As a Patient, I want to view my prescribed medicine so that I know what medicine I need to take | 6.1 6.2 6.3 6.4 | Develop prescribed medicine page Update database Code peer review Regression testing |  | X
7 | As a Patient/GP I want to be able to login to the Telemedicine platform, so that I can access the app’s services. | 7.1 7.2 7.3 7.4 7.5 | Implement Patient login page Implement GP login page Update database Code peer review Regression testing |  | X

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | As a super admin, I want to add a new user so that the user can access/use the ND Telemedicine platform. | #N/A | #N/A | #N/A | #N/A | #N/A
2 | As a super admin, I want to update user details so that user details are up to date. | #N/A | #N/A | #N/A | #N/A | #N/A
3 | As a super admin, I want to archive a user so that the user cannot access the ND Telemedicine platform. | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | As a patient i want to make an account on the app so that i can access the services of the app such as having contact with a doctor | #N/A | #N/A | #N/A | #N/A | #N/A
7 | As a Patient i want to add health information about me, so that my doctor can see my current health condition | #N/A | #N/A | #N/A | #N/A | #N/A
8 | As a Patient, I want to view my prescribed medicine so that I know what medicine I need to take | #N/A | #N/A | #N/A | #N/A | #N/A
9 | As a Patient/GP I want to be able to login to the Telemedicine platform, so that I can access the app’s services. | #N/A | #N/A | #N/A | #N/A | #N/A
10 |  | #N/A | #N/A | #N/A | #N/A | #N/A
11 |  | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 |  | #N/A | #N/A | #N/A | #N/A | #N/A
14 |  | #N/A | #N/A | #N/A | #N/A | #N/A
15 |  | #N/A | #N/A | #N/A | #N/A | #N/A
16 |  | #N/A | #N/A | #N/A | #N/A | #N/A
17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 |  | #N/A | #N/A | #N/A | #N/A | #N/A
20 |  | #N/A | #N/A | #N/A | #N/A | #N/A
21 |  | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A