## Product Backlog
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS
1 | As a super admin, I want to add a new user so that the user can access/use the ND Telemedicine platform. | Product Owner | High | 5 | IN PROGRESS
2 | As a super admin, I want to update user details so that user details are up to date. | Product Owner | High | 5 | IN PROGRESS
3 | As a super admin, I want to archive a user so that the user cannot access the ND Telemedicine platform. | Product Owner | High | 5 | IN PROGRESS
4 | As a patient i want to make an account on the app so that i can access the services of the app such as having contact with a doctor | Product Owner | High | 5 | IN PROGRESS
5 | As a Patient i want to add health information about me, so that my doctor can see my current health condition | Product Owner | High | 5 | IN PROGRESS
6 | As a Patient, I want to view my prescribed medicine so that I know what medicine I need to take | Product Owner | High | 5 | IN PROGRESS
7 | As a Patient/GP I want to be able to login to the Telemedicine platform, so that I can access the app’s services. | Product Owner | High | 5 | IN PROGRESS
8 | As a patient, I want to book an appointment with a doctor | Product Owner | High | 8 | TO DO
9 | As a doctor, I want to add my availabilities | Product Owner | High | 5 | TO DO
10 | As an admin, I want to send notifications to all users | Product Owner | Medium | 21 | TO DO
11 | As a patient, I want to make payments for my appointment | Product Owner | Low | 8 | TO DO
12 | As a patient, I want to view my appointment history | Product Owner | High | 8 | TO DO
13 | As a doctor, I want to be able to chat with my patients | Product Owner | Low | 8 | TO DO
14 | As a patient, I want to be able to chat with my doctor | Product Owner | Low | 8 | TO DO
15 | As a doctor, I want to prescribe medicine to a patient | Product Owner | High | 5 | TO DO
16 | As a patient, I want to view my payment history | Product Owner | Low | 5 | TO DO

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | As a super admin, I want to add a new user so that the user can access/use the ND Telemedicine platform. | #N/A | #N/A | #N/A | #N/A | #N/A
2 | As a super admin, I want to update user details so that user details are up to date. | #N/A | #N/A | #N/A | #N/A | #N/A
3 | As a super admin, I want to archive a user so that the user cannot access the ND Telemedicine platform. | #N/A | #N/A | #N/A | #N/A | #N/A
4 | As a patient i want to make an account on the app so that i can access the services of the app such as having contact with a doctor | #N/A | #N/A | #N/A | #N/A | #N/A
5 | As a Patient i want to add health information about me, so that my doctor can see my current health condition | #N/A | #N/A | #N/A | #N/A | #N/A
6 | As a Patient, I want to view my prescribed medicine so that I know what medicine I need to take | #N/A | #N/A | #N/A | #N/A | #N/A
7 | As a Patient/GP I want to be able to login to the Telemedicine platform, so that I can access the app’s services. | #N/A | #N/A | #N/A | #N/A | #N/A
8 | As a patient, I want to book an appointment with a doctor | #N/A | #N/A | #N/A | #N/A | #N/A
9 | As a doctor, I want to add my availabilities | #N/A | #N/A | #N/A | #N/A | #N/A
10 | As an admin, I want to send notifications to all users | #N/A | #N/A | #N/A | #N/A | #N/A
11 | As a patient, I want to make payments for my appointment | #N/A | #N/A | #N/A | #N/A | #N/A
12 | As a patient, I want to view my appointment history | #N/A | #N/A | #N/A | #N/A | #N/A
13 | As a doctor, I want to be able to chat with my patients | #N/A | #N/A | #N/A | #N/A | #N/A
14 | As a patient, I want to be able to chat with my doctor | #N/A | #N/A | #N/A | #N/A | #N/A
15 | As a doctor, I want to prescribe medicine to a patient | #N/A | #N/A | #N/A | #N/A | #N/A
16 | As a patient, I want to view my payment history | #N/A | #N/A | #N/A | #N/A | #N/A
17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 |  | #N/A | #N/A | #N/A | #N/A | #N/A
20 |  | #N/A | #N/A | #N/A | #N/A | #N/A
21 |  | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A